## Sheet1
VISTART JA - EU GA 676969
Month | 2015-10-10 | 2015-11-10 | 2015-12-10 | 2016-01-10 | 2016-02-10 | 2016-03-10 | 2016-04-10 | 2016-05-10 | 2016-06-10 | 2016-07-10 | 2016-08-10 | 2016-09-10 | 2016-10-10 | 2016-11-10 | 2016-12-10 | 2017-01-10 | 2017-02-10 | 2017-03-10 | 2017-04-10 | 2017-05-10 | 2017-06-10 | 2017-07-10 | 2017-08-10 | 2017-09-10 | 2017-10-10 | 2017-11-10 | 2017-12-10 | 2018-01-10 | 2018-02-10 | 2018-03-10 | 2018-04-10 | 2018-05-10 | 2018-06-10 | 2018-07-10 | 2018-08-10 | 2018-09-10
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP1 - Coordination WP Leader: ISS - CNT - CNS (IT) | 2015-11-10: Steering Commitee set up; 2016-03-10: MS.25 Production of Financial Guide; 2016-09-10: MD.1 First intermediate technical and financial report; 2017-09-10: MD2 Second intermediate technical and financial report; 2018-06-10: D1.3 Sustainability plan; 2018-09-10: D1.4 Final implementation and Financial report
WP2 - Dissemination WP Leader: HNBTS (OVSZ - HU) | 2016-01-10: MD3. Layman Brochure; 2016-03-10: D2.1 Dissemination Plan; 2016-09-10: MS.3 First Newsletter; 2018-01-10: MS.4 Second Newsletter; 2018-09-10: MD5. Layman version of the Final Report
MD4. Website
WP3 - Evaluation WP Leader: NRSCDVH (RO) | 2015-12-10: D3.1 Final Evaluation Plan including setting up of External Advisory Board; 2017-03-10: D3.2 Intermediate Evaluation report; 2018-09-10: D3.3 Final Evaluation report
MS.27 Establishment of External Advisory Board
|  |  | MS.5 Draft evaluation plan including evaluation tools, success criteria, indicators, timing and responsibilities | [8 empty] | MS.6 Intermediate evaluation report. Report on month 12 monitoring and evaluation processes for all the activities and deliverables
MS.7 Evaluation Report after each key deliverable is delivered
WP4 - Vigilance Reporting for Blood, Tissues and Cells WP Leader: IPST (PT) | 2015-11-10: MS.28 Establishment of SARE reporting working group; 2016-03-10: MS.29 Establishment of RATC/new risks working group; 2016-06-10: MS.8 Exploratory workshop on RATC/new risks held; 2016-09-10: D4.2 Results of Exploratory Workshop on management at national level of rapid alerts circulated via EU RATC platform and recommendations for harmonised procedures; 2017-01-10: D4.1 Unified common approach on SARE reporting for annual reporting to EC; 2018-05-10: D4.3 Guideline on responding to new risks
[7 empty] | April 21-22 Lisbon |  |  |  |  | MS.9 Draft of Common Approach for SARE Reporting sent to all CAs for comments
WP5 - International collaboration for Vigilance Communication and Preparation Process Development WP Leader: ISS - CNT (IT) | 2015-12-10: MS.10 Expert group on Notify case identification and submission established (Part A working group); 2016-07-10: MS.12 A standard form/checklist (similar to the PPD) for quality evaluation of new processing methods (Part B); 2016-09-10: D5.3 Draft Principles for Competent Authorities for the evaluation and approval of clinical follow up protocols for blood, tissues and cells prepared with newly developed and validated processing methodologies (Part B); 2016-12-10: D5.1 Guidelines for CAs on how to prepare SARE cases of didactic value for insertion in the Notify library (Part A); 2017-05-10: MS.11 Establishment of a network of vigilance officers to analyse the case investigations (Part A); 2017-09-10: D5.4 Principles for Competent Authorities for the evaluation and approval of clinical follow-up protocols for blood, tissues and cells prepared with newly developed and validated processing methodologies (Part B); 2018-06-10: D5.2 Report on SARE investigation networking exercise (Part A)
|  |  | MS.30 Establishment of Part B working group | January 18 Rome |  |  |  | May 20 Rome
WP6 - An operational manual for blood, T&C CAs WP Leader: ANSM (FR) | 2015-12-10: MS.31 Design of Survey (4 or 6 technical meetings - one in Rome- tbd); 2016-03-10: March 24-25 Budapest; 2016-05-10: May 18-19 Rome; 2016-09-10: MS.13 Draft document circulated to CAs for comments; 2017-01-10: D6 Final operational manual for EU CAs responsible for the inspection and authorization of blood and TEs
WP7 - Training of blood, T&C inspectors with sharing of expertise across MS WP Leader: ISS - CNT - CNS (IT) | 2015-12-10: MS.31 Design of Survey; 2016-02-10: MS.32 Final Deadline for gathering Survey information; 2016-03-10: D7.1 Results report; 2016-07-10: MS.14 Design of course content; 2017-04-10: MS.15 First training course; 2017-11-10: Discussion on proposals for an international register of EU trained inspectors with guidelines for international certification of inspectors for participation in joint inspections; 2018-05-10: MS.16 Second training course; 2018-07-10: D7.2 Proposals for common requirements for registration and acceptance EU inspectors on an EU registry of international blood, tissues and cells and ART inspectors. Requirements for EU register of inspectors of blood, T&C inspectors
WP8 - Establishment of a framework for joint inspections WP Leader: MOH RC (HR) | 2016-12-10: MS.33 1st Plenary Workshop for CAs (back-to-back TC CA meeting); 2017-04-10: MS.34 2nd Plenary Workshop for CAs (back-to-back TC CA meeting); 2017-06-10: MS.18 5 inspections within EU countries will be held from M21 to M27 - Associated with each inspection, there will be a small specific group workshop (pre-inspection and post-inspection) analysing the plan and the experience; 2018-01-10: MS.17 Circulation of the draft Code of Practice on Joint MS Inspection to all MS CAs for Comments; 2018-05-10: D8.1 Code of Practice on Joint MS inspections; 2018-09-10: D8.2 Reports on lessons learned from Joint Inspections
WP9 - A Voluntary Programme of Inter-MS Inspection System Auditing WP Leader: HPRA (IE) | 2017-05-10: MS19: Define the process and criteria for verification of quality management and inspection performance in accordance with the new guidelines developed by WP6; 2017-09-10: D9.1 Production of teaching material for auditor training programme; 2017-11-10: MS21: CESIP training course (2 days); 2018-01-10: MS35: Performing 3 audits (one pilot Audit from M28 to M32); 2018-07-10: D9.3 Report of outcome of CESIP programme (including outcomes of initial pilot audit, training course and performed audits)
[20 empty] | MS20: Define a training programme for auditors |  |  |  | D9.2 Proposals for the ongoing resourcing of CESIP post JA
WP10 - Implementation of the Single European Coding system in tissue establishments WP Leader: ISS - CNT - CNS (IT) | 2015-11-10: MS.36 Enquire to CAs for onsite SEC implementing support visits and their prioritization; 2016-01-10: MS.22 E-learning module content designed; 2016-03-10: MS.23 e-learning module from M6 to M10 open for 4 months; 2016-05-10: MS.24 Programme for participation in scientific congresses defined and agreed with congress organisers; 2016-07-10: MS.38 4 Workshops to be held at months 6, 10, 14, 16; 2016-09-10: MS.27 Training course; 2016-11-10: MS.38 4 Workshops to be held at months 6, 10, 14, 16; 2017-01-10: MS38 4 Workshops to be held at months 6, 10, 14, 16; 2018-08-10: D10.2 Report of results of training course, performed support visits and held workshops
[6 empty] | MS38 4 Workshops to be held at months 6, 10, 14, 16 | [5 empty] | D10.1 Teaching material for e-learning module and face to face residential course
EBMT Congress: April 3- 6 Valencia
LEGEND
D. Confidential | 2015-10-10: D. Public
MS = Milestone | bar: 2015-10-10
D = Deliverable
MD = Mandatory Deliverable
The Part B WG will meet in 4 occasions (two before D5.3 and 5.4)
Meeting
MS.2
Intemediate Plenary Meeting
Rome tbd
MS.26
Final Plenary Meeting
Budapest tbd
MS.1
Kick Off
Luxembourg
12-13 Ott
Meeting to agree on the evaluation plan and to distribute the evaluation tool for comments and review
Meeting for presentation, comments and review of intermediate report
1st meeting Part A WG held (on a total of 6 meetings at least two of these in Portugal with WP4 meetings)
The group will have a technical meeting to define contents of training course and associated partners will meet a second time to define the contents of workshops to be held at professional societies congresses
The group will meet on
at least 5 occasions tbd
It will meet on 3 occasions: one is Exploratory Workshop (others tbd)
Up to 7 on site visits for the support of CAs with SEC - tbd
Final technical meeting tbd
Final Consensus meeting tbd
1st Technical meeting – in conjunction
with WP6: February
8-11 Rome
2nd Technical meeting: May 16-17 Rome
3rd Technical meeting tbd
4th Technical meeting (tbd after the course)